## Sheet1
Limerick Institute of Technology
Institiuid Teicneolaiochta Luimnigh
Project Schedule for Academic Year 2020/2021
Week No. | Beginning | Deadline
2 | 2020-09-07
3 | 2020-09-14 | Project Initiation
4 | 2020-09-21
5 | 2020-09-28
6 | 2020-10-05
7 | 2020-10-12 | Current Services Description - Friday 16th October 2020
9 | 2020-10-19
10 | 2020-10-26 | Use Case Specifications 1st (Iteration) - Friday 30th October
11 | 2020-11-02
12 | 2020-11-09
13 | 2020-11-16 | Prototyping - Monday 16th October & present this week to supervisor
14 | 2020-11-23 | Database Definition - Sunday 27th December 2020
15 | 2020-11-30 | Project Implementation Starts - Monday 30th November 2020
16 | 2020-12-07
17/18/19 | Christmas Holidays
20 | 2021-01-04
21 | 2021-01-11 | Activity Diagrams - Friday 15th Jan 2021
22 | 2021-01-18
23 | 2021-01-25 | Project Implementation Ends Friday 29th Jan 2021
24 | 2021-02-01 | Customer acceptance testing this week
25 | 2021-02-08
26 | 2021-02-15
Formulas:
Beginning = +[Beginning, row above]+7